## Coversheet (hidden)
WNS Global Services (P) Ltd.
Issue/Product Log for Transamerica
Date | Version No. | Summary of Changes

## Release Tracker
Transamerica Desktop Automation:: Release Plan
| Type | Open | Feasability Check | Resolved | Under Approval | Approved | Planned | In-Progress | Released / Closed | Cancelled | Duplicate | Hold |  | Priority | Count
| Issue/Bug | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | Critical | 0
| Change Request-AllTowers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | High | 0
| Change Request-Specific Tower | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Medium | 0
| Query | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Low | 1
| Configuration Change | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Total | 1
| TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
|  |  |  | Effort (Person Days) |  |  |  | TOTAL Effort (Person Days) | Requirements Start Date | Requirements End Date | Dev End Date | Testing End Date | UAT / Issue Fixing End / UAT Sign-off Date | Production Movement / Go-Live | Release Status | Remarls
| Release # | Release # | Release Count | Requirements | Devp + Testing | UAT + Issue Fixing | Production Deployment
| Bank Recon | 1.1 | 1 | 0.5 | 2 | 3 | 0.5 | 6 | 2017-03-30 | 2017-03-30 | 2017-04-03 | 2017-04-03 | 2017-03-06 | 2017-04-07 | Completed
|  |  | 0 | - | - | - | - | 0
|  |  | 0 | - | - | - | - | 0
|  |  | 0 | - | - | - | - | 0
|  |  | 0 | - | - | - | - | 0
|  |  | 0 | - | - | - | - | 0
|  |  | 0 | - | - | - | - | 0
|  |  | 0 | - | - | - | - | 0
|  |  | 0 | - | - | - | - | 0
|  |  | 0 | - | - | - | - | 0
0
|  | In -Progress | Completed
Sr No | Ticket# | Issue/Change Request/Query Description | Issue/CR Raised Date | Raised By (Requestor) | Tool Name | Type | Preferred Release # | Priority | Status | Actual Release # | Effort (Person Days) | Chargeable | Resolve Date | Target Closer Date | Plan | Remarks | OPS feedback from testing
SAMPLE | 000000001 | There should be one criteria code in coding master. If criteria code found duplicate , then tool will ignore duplicate criteria and proceed, and such duplicate count will popup as warning to user. User has to inform admin to remove such duplicate from coding master. | 2015-12-17 | Natacha | Bank Recon | Issue/Bug | 1.1 | Low | Released / Closed | 1.1 | 2.5 | No | 2017-04-03 | 2017-04-07 | 1) Development - 3-Apr-17 2) UAT Release - 6-Apr-17 3) Over all user testing -06-Apr-17 5) Go-live - 7-Apr-17
Note on L28: Req,Development & Testing (Excluding UAT and deployment effort)

## Sheet1 (hidden)
Count of Status | Status
Tool Name | Cancelled | In-Progress | Open | Released / Closed | Resolved | (blank) | Grand Total
Bank Recon | 1 | 11 |  |  |  |  | 12
GL Recon Phase2 |  |  | 1 | 16 |  |  | 17
MEC Tracker |  | 1 |  | 9 | 1 |  | 11
(blank)
Grand Total | 1 | 12 | 1 | 25 | 1 |  | 40